

# **IRAMM**

Mesa Community College (MCCCD)

Central Arizona College (CAC)

Pima Community College (PCC)

The purpose of this Progress Report is to give consortium partners interim feedback on the status of their grant project(s). This report covers the period from the beginning of the grant through September 31, 2021. \*

*\*Data captured in this forecasting tool has been adjusted and is made available as an example for other grantees to build their own tool.*

## **Participant Outcomes Progress to end of September 2021**

### Mesa Community College

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer Partner | Date Active | Outcome A-1 | Outcome A-2 | Outcome A-3 |
| A-1 Airlines Pre-Apprenticeships | 10/1/2018 | 50 | 0 | 0 |
| A-1 Airlines Composites | 10/1/2018 | 13 | 7 | 3 |
| Steel Associates | 12/1/2020 | 15 | 15 | 7 |

Central Arizona College

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer Partner | Date Active | Outcome A-1 | Outcome A-2 | Outcome A-3 |
| ABC Copper | 3/1/2020 | 23 | 15 | 11 |
| Nutritional Products Production, Inc. | 5/1/2017 | 14 | 10 | 8 |
| Ole’ Time Whiskey Products | 7/1/2021 | 2 | 2 | 2 |
| Electric Motors | 12/1/2019 | 12 | 11 | 9 |

### Pima Community College

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer Partner | Date Active | Outcome A-1 | Outcome A-2 | Outcome A-3 |
| Aerospace & Defense Technologies | 9/1/2018 | 15 | 12 | 7 |
| Optical Electronics and Technologies | 5/1/2017 | 2 | 2 | 0 |
| Avionics Aviation Services | 7/1/2021 | 2 | 1 | 1 |
| Neon Lighting & Signs | 12/1/2019 | 8 | 5 | 3 |

## **Match Contribution Progress**

|  |  |  |  |
| --- | --- | --- | --- |
| Source of the Match (Partner) | Amount Received (Actuals) | Match Required at End of Grant (Projected) | Remaining Balance |
| MCC | $78,179 | $150,000 | $71,821 |
| CAC | $50,633 | $130,000 | $79,367 |
| PCC | $908,000 | $1,500,000 | $592,000 |
| **TOTAL** | **$1,036,812** | **$1,780,000** | **$743,188** |